# Title III 5- Year Proposal

Covering October 1, 2017 – September 30, 2022

Project Director: Renita Luck

| 1. Name of Institution: Albany State University | 2. Activity Title: Quality Academic Instruction for Underrepresented Populations 3. Activity Number: To be completed by the Office of Title III |
| --- | --- |
| 4. Focus Area: Academic Quality, Student Services, and Outcomes | 5. LAA Category: Telecommunications technology equipment or services and program materials, , faculty development, delivery of academic instruction in disciplines in which Black Americans are underrepresented, and student service programs. |

Budget Request Amount:  $		151,418.00

6.  Narrative

A.  INTRODUCTION

Asynchronous online learning opportunities continue to grow at both public and private higher education institutions (Quality Matters & Eduventures, 2017). In fact, survey results conducted by Quality Matters and Eduventures revealed that one in 14 students enrolled at four-year public institutions are participating in coursework fully at a distance (2017). During the fall 2016 semester, 63 percent of Albany State University’s Gillionville Campus student population were involved in online learning with 32 percent being fully online students. (Online data for Albany State University’s Radium Springs Campus during the same time was not tracked.) During the summer 2017 semester (before final B Term enrollments), Albany State University had an overall enrollment of 2,847 with 41 percent (1178) being fully online.

Historically Black Colleges and Universities (HBCU’s) have lagged in the development of distance learning opportunities as compared to non-HBCU institutions (Flowers, White, & Raynor, 2012) even though African American and other minority populations entering post-secondary education continues to rise (U.S. Department of Education). Albany State University’s mission is to become a premiere, first-choice University and as such must invest in innovative delivery modalities and instructional methods to reach our 26 county area and beyond. Distance learning is highly competitive (Quality Matters & Eduventures, 2017) and excellence in course design, instruction, and interaction will differentiate Albany State University’s distance learning courses and programs from the vast majority of offerings available to choose from.

In order to facilitate the demand for distance learning opportunities with the appropriate infrastructure that will ensure academic rigor and quality, Albany State University (ASU) must respond now by implementing practices and procedures that ensure solid course development, engaging, interactive course content, and responsive, comprehensive student support. The following proposed activities will allow ASU to enhance existing distance learning resources, as well as build new infrastructures that will position the University as a strong competitor among distance learning institutions and as a first choice for students seeking distance learning opportunities.

B. alignment with Institutional Strategic Plan

Transactional Distance Theory posits that for distance learning courses to be effective three elements must be present, structure, autonomy, and presence (Moore, 1993). As a University, if we embrace this theory, focus must be on structure and presence as student autonomy is an unknown and uncontrollable variable. Ensuring that underrepresented populations not only are afforded distance learning opportunities, but also are presented with high quality, rigorous course work requires professional development for stakeholders involved in course development and delivery, resource tools for the creation of interactive, engaging content, and human resources for student and faculty support.

One of Albany State University’s strategic goals is to aspire to excellence in teaching and learning and to garner recognition as a premier southern regional university (Strategic Plan Document). Additionally, ASU has identified additional strategic goals, including the need to expand access to Higher Education by “offering flexible class times and instructional modalities” and the need to “elevate historically underserved populations” (CITE). By expanding the development of high-quality distance learning opportunities and its underlying infrastructure, ASU will increase its ability to provide synchronous and asynchronous instructional modalities to all potential student populations.

C.  alignment to Title III Purpose

Innovative delivery methods such as online or video conferencing allows the university to reach diverse populations who are unable to relocate geographically or travel to campus routinely to attend class. However, as stated previously innovative delivery methods alone are not enough, the instruction offered regardless of modality must be of the highest quality and rigor to ensure competitive graduates and loyal alumni. Distance learning offerings must be infused with interactive, engaging content delivered by committed instructors, and supported with appropriate staff services to bridge geographical distances and communication challenges. Distance learning programs which ensure quality, rigor, and support services are in place and assessed for continuous improvement opportunities are certain to enhance a university’s enrollment, retention, and graduation rates.

D.   OVERVIEW OF OBJECTIVES AND IMPLEMENTATION STRATEGY

Objective 1

Increase instructor presence in 35% of online, undergraduate classrooms through the use of innovative delivery methods for faculty lectures.

Explanation:

Instructor presence in the online classroom is increased when students are able to connect to the instructor through visual and/or audio experiences (CITE). By providing cutting edge, but simply to use technologies and resources and support for instructors, online video and audio lectures will be easier to produce and should be more widely adopted. Proposed for this objective are the following:

- One portable Lightboard. A Lightboard is a transparent board that allows an instructor to write, diagram and project information to students without having to turn away from the camera. This allows the instructor to graphically and audibly represent material without losing eye contact with his or her audience.

Implementation Strategy:

The use of a Lightboard in a lecture will closely simulate a face-to-face experience for both the students and instructors and will increase teacher presence and teacher to student interaction in online classrooms. A portable Lightboard will be purchased so that the technology is mobile. Training will be provided for distance learning personnel to understand the Lightboard’s video requirements and also to ensure proper care and maintenance of the board. Information sessions will be held for faculty members to come see and experiment with the Lightboard. Distance learning will identify and strongly encourage instructors teaching in key disciplines, such as computer science, math, and courses with labs to implement this method of lecture instruction in online classes. The Lightboard will be available to use by appointment for all online courses and programs.

- Softchalk ELearning Authoring Tool. Softchalk is a program that allows instructors to create interactive, engaging content. Additionally, Softchalk has integrated eBook creation into its software package that will allow instructors to more easily create open educational resources for their courses, which has the potential to reduce overall educational costs for students.

Implementation Strategy:

Using Softchalk to create lecture materials will allow instructors to build interactive experiences right into the lecture presentation. SoftChalk will allow the instructor to include audio (thus increasing teacher presence) and engage the students with on-screen activities (thus increasing student-content interaction) that has proven to effectively increase student learning and retention of course materials (Mayer, 2016). Distance Learning will hold training sessions for instructors in the use of SoftChalk and will provide assistance in the creation of SoftChalk lectures and integration with the learning management system.

- VoiceThread. VoiceThread is an audio integration for the learning management system that will allow discussions to occur asynchronously through audible conversations. Students and instructors will be able to leave audio responses to question prompts and interact in the same way as on a printed discussion board, but through the use of audio files. VoiceThread only requires basic computer hardware, including a microphone, and does not require students to download or purchase additional software.

Implementation Strategy:

VoiceThread implementation will increase student-to-student and student-to-instructor interaction and presence in the online classroom. To implement VoiceThread distance learning personnel will provide live training, printed and video tutorials for instructors and students alike.

- VideoScribe VideoScribe is a video software tool that will allow distance learning staff and instructors to create high-definition, whiteboard style animation videos. VideoScribe is easy to use and requires no design or technical knowledge to operate.

Implementation Strategy:

VideoScribe videos are engaging and allow the creator of the video to use a multitude of resources to produce professional results. VideoScribe videos are exceptionally suited for 2 to 5 minute videos describing specific concepts or ideas. Distance Learning staff will provide training opportunities for instructors and will also work with instructor content to produce these engaging videos. The movement, audio, and style of VideoScribe videos should appeal to ASU’s distance learners and increase student engagement with content and teacher presence through multimedia presentations.

- Video Conferencing Hardware/Software. Currently ASU has off site instructional locations at Cairo and Waycross. These locations do not have video conferencing availability, which means that instructors must be on-location to teach or students who prefer the face-to-face modality must take online courses. By providing video conferencing resources to all off-site locations, ASU faculty members will be able to teach face-to-face from main campus locations to offsite locations when necessary.

Implementation Strategy:

The video conferencing equipment will be installed at the offsite locations in ASU designated classroom space. Training will be provided to distance learning staff and instructional faculty in the appropriate use of the equipment. Distance Learning will work with the Academic Departments to determine which courses would work best utilizing the video conferencing delivery. The use of the video conferencing delivery mode to enable scheduling of courses across multiple locations will increase enrollment opportunities at all off site locations as the need to cancel scheduled courses will decrease.

- Distance Learning Faculty Support Specialist. This will be a full-time position working with faculty to ensure full integration of the above resources as well as existing and emerging resources for distance learning course delivery.

Implementation Strategy:

The Distance Learning Faculty Support Specialist (DLFSS) will work full-time reporting to the Executive Director of Distance Learning. Orientation and training will be provided to the DLFSS who will in turn, provide orientation and training to instructional faculty on LMS related academic technologies. Additionally, the DLFSS will create and maintain a repository of multimedia tutorials surrounding the use and manipulation of academic technologies. The DLFSS will serve as the secondary learning management system administrator and will work closely with Distance Learning instructional design teams.

Objective 2

Increase student to content engagement by 45% by increasing access to tutoring and support services that promote student autonomy.

Explanation:

Student to content engagement is a critical success element in distance learning opportunities (Mayer, 2016). By increasing access to resources that may be independently accessed anytime/anywhere, the university will increase student to content engagement. Additionally, self-determination theory posits that student autonomy may be taught if opportunities for self-directed learning and instruction are provided (CITE), which will help to decrease transactional distance and increase student success (Moore, 1993). The following resources are to support this increase in student to content engagement:

- Grammarly Subscriptions. Grammarly is a writing/plagiarism detection tool that works in tandem with Turnitin (which the university already has integrated within the learning management system) to provide students with a resource to self-check grammar, punctuation, and plagiarism mistakes prior to submission of assignments.  Grammarly can be used as a standalone tool accessed through the Internet, or installed on the student’s computer and integrated fully into word processing software.

Implementation Strategy:

The use of Grammarly will allow students to self-check written work prior to submission for grammar and punctuation errors, as well as for instances of plagiarism.  Grammarly works in conjunction with Turnitin as a plagiarism checker and will assist students in ensuring that plagiarism mistakes such as failure to use quotation marks accurately are caught prior to submission. Additionally, Grammarly will work as a grammar coach providing suggestions and brief tutorials on common punctuation and grammar mistakes. Training will be provided to students and faculty members on the download, installation, and use of Grammarly.

- Atomic Learning. Atomic Learning is online training that can be utilized by both students and faculty members. Student training videos range from personal development such as overcoming test anxiety and strategies for working in a group to gaining technical skills including working in Office or Google groups or manipulating the features of a learning management system to optimize learning. Atomic Learning provides just in time training for students anytime/anywhere Internet access is available.

Implementation Strategy

Atomic Learning will be promoted to distance learners, but may be utilized by all learners regardless of modality. Training will be provided on its use to both students and faculty members. Monthly reminders will be sent to all stakeholders highlighting key training videos to promote use. When appropriate, assistance will be provided by the distance learning office to integrate videos into classroom instruction.

Objective 3

Increase professional development attendance and training opportunities for excellence in distance teaching and learning and student support by 35%.

Explanation:

To teach and support students in the distance learning environment requires specific skills and knowledge to be effective (Mayer, 2016). In order to ensure high quality academic instruction and student support services in this modality, professional development for instructors, supporting staff, and administrators is necessary. The following is proposed to support this objective, and while this may seem like an extensive list the attendees vary from among distance learning staff members to faculty involved in distance learning activities.

- Educause Conference Attendance.  The Educause annual conference brings together post-secondary educators from across the world to share expertise and network. The conference routinely presents information on emerging technologies and theories specific to distance learning.

Implementation Strategy:

The Educause Conference will be an opportunity for the Distance Learning Support Specialists, members of the Instructional Design Team, Distance Learning Faculty Support Specialist, and/or administrators of distance instructional faculty to network and learn about emerging theories and technologies for use in the distance learning environment.  Members who attend the conference will be expected to produce an executive summary of the experience and to provide training for other distance learning team members or faculty as appropriate.

- ELearn Conference Attendance. The ELearn annual conference is promoted as a “world conference” that is presented by the Association for the Advancement of Computing in Education (AACE). This is an international conference that brings together leaders in distance learning to discuss the latest research, development, applications and issues in distance learning.

Implementation Strategy

The ELearn conference will be an opportunity for members of the Instructional Design Team, Administration or Distance Learning faculty to network with a global audience and bring home information and resources surrounding emerging research and distance learning strategies. Information derived from this conference will enhance student outcomes in the distance learning environment as attendees will return and provide training to appropriate audiences and implement resources as appropriate in distance learning instruction.

- Georgia Summit. The Georgia Summit is an annual conference hosted by the University System of Georgia covering topics ranging from INGRESS and LMS issues to teaching and learning strategies for distance learning.

Implementation Strategy:

This conference will greatly benefit the work of the LMS Administrator, the Distance Learning Support Specialists, and/or other members of the distance learning team. Information garnered from this conference can directly affect the utilization of the LMS and process and procedures in the distance learning office that directly impact student success. Members attending this conference will return with valuable knowledge to share through training opportunities and/or resources to immediately implement in the distance learning environment.

- Rock Eagle. Rock Eagle is a technology conference hosted by the University System of Georgia. Detailed and specific LMS information is routinely covered at this conference and it is necessary for the LMS administrator to attend this conference annually.

Implementation Strategy

The LMS administrator(s) will attend this conference annually, complete an executive summary upon return, and implement as required resources obtained at the conference in the distance learning environment.

- D2L Fusion. D2L Fusion is an annual conference hosted by BrightSpace that presents information, resources, and updates to the learning management system used by the university. It is highly beneficial for the LMS administrator to attend this conference.

Implementation Strategy

The LMS administrator(s) will attend this conference annually, complete an executive summary upon return, and implement as required resources obtained at the conference in the distance learning environment.

- SITE Conference. The SITE Conference is hosted by the Society for Information Technology and Teacher Education and presents information about the use of information technology in teacher education and faculty/staff development.

Implementation Strategy

Distance Learning administration will attend this conference to garner information on theoretical and research knowledge, and professional practice in distance learning environments for using technology in teacher education and faculty/staff development. Upon return from this conference, attendee(s) will present training opportunities to the appropriate faculty, staff, or student groups.

- WCET Annual Meeting/SAN Conference. WCET is the leader in State Authorization regulations and practices for distance learning. The annual meeting is held in conjunction with State Authorization Network (SAN) meetings and should be attended by distance learning administration to ensure appropriate measures are taken for university compliance with state authorization requirements.

Implementation Strategy

Distance Learning administration will attend this conference to garner information on emerging state authorization requirements and will implement needed changes to existing policies and practices as required upon return from the conference.

- Quality Matters Annual Conference. ASU has adopted Quality Matters as its standard of excellence for online learning. Implementation includes onsite training for faculty members in the Applying the Quality Matters Rubric, online training in Peer Review Training, and in-house subscriber based reviews of developed and redeveloped online courses.  This annual conference allows university personnel to receive information from Quality Matters and provide feedback about the process and policies. It is a time to network, share ideas and garner resources and important information that will enable QM implementation to continue successfully at the university.

Implementation Strategy

The Quality Matters annual conference will be attended by faculty or staff members who are fully engaged in the QM implementation strategies for the university. Conference attendee(s) will complete an executive summary covering the learning gained at the conference and share information and ideas with the QM implementation and course review teams.

- Miscellaneous Conference Opportunities. It is impossible to comprehensively cover all opportunities that may arise and be beneficial for distance learning stakeholders in the coming year. This line item would cover any distance learning focused conference, summit, or gathering that would convey information and/or resources about emerging resources, research, trends, technology, pedagogy, andragogy, or theories related to distance learning.

Implementation Strategy

Attendee(s) would vary with the conference type, but would consist of faculty, students or staff involved in furthering the academic quality of distance education at the university. Attendee(s) would present an executive summary of the event and provide training as appropriate upon return.

E.  KEY PERSONNEL

The activity director will be Mrs. Renita Luck, M.Ed., Executive Director of Distance Learning. (CV is attached). Other key personnel include distance learning staff members who will participate in the assessment and implementation of the activity objectives.  These members include:

- Distance Learning Support Specialists: Cheryl McNeal, Jennifer Nelms, Mary Elizabeth Thompson

- Enrollment Coordinator: Denata Williams

- Offsite campus liaison: Sarah Rogers

- LMS Administrator: David Evarts

- Distance Learning Technical Support Specialist: Latrisha Batten

One personnel position is being requested through this proposal that of a Distance Learning Faculty Support Specialist (DLFSS). The Distance Learning Faculty Support Specialist will be an expert in the learning management system and integrated resources used for teaching and learning. The DLFSS will assist faculty with integration and implementation of academic technology to ensure high levels of academic quality and student success in distance learning environments.

Currently, the duties this position will assume are being fulfilled by the distance learning support specialist, LMS administrator, and other Executive Director of Distance Learning. This additional workload for the support specialist and LMS administrator reduces available time and resources for the implementation of proactive intervention strategies that promote student success in distance learning. This position would fulfill an identified and crucial need for faculty support in academic technology as we continue to develop and redevelop courses and programs for online delivery. This position will work closely with the instructional design team to ensure that academic technology is integrated and implemented correctly and that appropriate tutorials and training are provided to all stakeholders.

F.   ASSESSMENT PLAN

Objective 1

Increase instructor presence in 35% of online, undergraduate classrooms through the use of innovative delivery methods for faculty lectures.

Assessment:

For the fall 2017 semester, ASU has 130 faculty members scheduled to teach 126 unique online courses, and while this number will drop somewhat for the spring 2018 term it is a good baseline number to work with when determining assessment data for this objective. The initial implementation of the objective will be considered successful if a minimum of 25 unique distance learning courses have utilized at least one of the lecture resources/strategies outlined by this objective within six months of purchase.

The overall implementation of this objective will be considered successful if at least 44 unique distance learning courses have utilized at least one of the lecture resources/strategies outlined by this objective within twelve months of purchase.

Objective 2

Increase student to content engagement by 45% by increasing access to tutoring and support services that promote student autonomy.

Assessment

The success of this objective will be measured by student use of the identified resources/strategies. The objective will be considered successful if at least 45% of the online student population (unique users) access at least one of the resources during the academic year the resources are implemented.

Objective 3

Increase professional development attendance and training opportunities for excellence in distance teaching and learning and student support by 35%.

Assessment

Assessment for this objective will be based on the following variables:

- Variety of attendees. In order for conference attendance to count as professional development for a department or program there should be opportunities for multiple individuals to participate. Therefore, one variable for assessment of this objective will be the variety of individuals that attend conferences/training throughout the academic year. To be considered successful on this portion of the assessment no less than three different distance learning stakeholders should participate in one of the listed professional development opportunities.

- Training. In order for conference attendance to truly count as professional development the information should be shared among appropriate stakeholders and/or resources/strategies should be appropriately integrated into operations upon return. To be considered successful on this portion of the assessment, one training session should be offered to the appropriate stakeholders by the conference attendee(s) within four weeks of the conference’s conclusion and/or an executive summary should be provided to the Executive Director of Distance Learning on the outcomes of the conference and the integration of the appropriate resource/strategy.

G. INSTITUTIONALIZATION PLAN

Objective 1

Increase instructor presence in 35% of online, undergraduate classrooms through the use of innovative delivery methods for faculty lectures.

Institutionalization Plan

Annual support/maintenance fees for the resources listed under this objective will be institutionalized through the use of eTuition funds resulting for eTuition rates garnered from ASU online courses as well as from additional funds obtained from student participation in eCore and eMajor. Each year at least one annual maintenance fee should be moved from grant funded to state funded until all annual licensing is being paid through state funded resources.

The Distance Learning Faculty Support Specialist position will be institutionalized through the use of eTuition funds and funds made available through increased enrollment. It is expected that this position will enhance the academic quality of distance learning instruction that will result in enrollment growth in online courses as well as at off-site instructional locations.

Objective 2

Increase student to content engagement by 45% by increasing access to tutoring and support services that promote student autonomy.

Institutionalization Plan

The annual licenses fees for the programs listed under this objective will be institutionalized through this use of eTution funds, eCampus revenues, and student technology fees. One program’s license fee should be moved to state funded under the revenue sources listed above with 2 ½ years and the remaining program by the end of the 5 year cycle.

Objective 3

Increase professional development attendance and training opportunities for excellence in distance teaching and learning and student support by 35%.

Institutionalization Plan

Professional development and training will dramatically enhance the academic quality and rigor of distance course delivery. This increase in quality will result in growth in both online and offsite instructional site student populations. The enrollment growth should provide enough funds for the professional development opportunities to continue under the distance learning state funded budget. The move to state funded for each of these conferences will be at the end of year two and culminate at the end of the grant’s life-cycle.

## ACTIVITY OBJECTIVES AND ANTICIPATED RESULTS

# Grant Period:

(Objectives and performance indicators must be stated in measurable terms)

| 1. Name of Institution: Albany State University | 2. Activity Title: Quality Academic Instruction for Underrepresented Populations 3. Activity Number: 1 (Title III, Part B) |
| --- | --- |
| 4. Activity Objective(s) | 5. Anticipated Results to Measure Success (Performance Indicators): |
| Objective 1: Increase instructor presence in 35% of online, undergraduate classrooms through the use of innovative delivery methods for faculty lectures. | Performance Indicator 1: The initial implementation of the objective will be considered successful if a minimum of 25 unique distance learning courses have utilized at least one of the lecture resources/strategies outlined by this objective within six months of purchase. The overall implementation of this objective will be considered successful if at least 44 unique distance learning courses have utilized at least one of the lecture resources/strategies outlined by this objective within twelve months of purchase. |
| Objective 2: Increase student to content engagement by 45% by increasing access to tutoring and support services that promote student autonomy. | Performance Indicator 2: The success of this objective will be measured by student use of the identified resources/strategies. The objective will be considered successful if at least 45% of the online student population (unique users) access at least one of the resources during the academic year the resources are implemented. |
| Objective 3: Increase professional development attendance and training opportunities for excellence in distance teaching and learning and student support by 35%. | Performance Indicator 3: Assessment for this objective will be based on the following variables: • Variety of attendees. In order for conference attendance to count as professional development for a department or program there should be opportunities for multiple individuals to participate. Therefore, one variable for assessment of this objective will be the variety of individuals that attend conferences/training throughout the academic year. To be considered successful on this portion of the assessment no less than three different distance learning stakeholders should participate in one of the listed professional development opportunities. • Training. In order for conference attendance to truly count as professional development the information should be shared among appropriate stakeholders and/or resources/strategies should be appropriately integrated into operations upon return. To be considered successful on this portion of the assessment, one training session should be offered to the appropriate stakeholders by the conference attendee(s) within four weeks of the conference’s conclusion and/or an executive summary should be provided to the Executive Director of Distance Learning on the outcomes of the conference and the integration of the appropriate resource/strategy. |

| # GRANT ACTIVITY FOR THE TITLE III PART B OR PART F PROGRAMS |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| IMPLEMENTATION STRATEGY AND TIMETABLE FORM |  |  |  |  |  |  |
| # NAME OF ACTIVITY COORDINATOR AND OFFICE: Renita Luck, Executive Director, Distance Learning |  |  |  | 2. Activity Title: Quality Academic Instruction for Underrepresented Populations |  |  |
| 3. SPECIFIC TASKS TO BE COMPLETED | 4. PRIMARY PARTICIPANTS | 5. METHODS INVOLVED | 6. TANGIBLE RESULTS |  | 7. timeFRAME FROM/TO |  |
| 1.1 Purchase LightBoard, provide training, and begin creating lectures for distance learning delivery | Executive Director Instructional Design Teams Distance Learning Technology Support Specialist Faculty Members | Establish a schedule of trainings to promote the use of the LightBoard for distance learning lectures. Establish a method for scheduling appointments to create lectures using the equipment. | An increase in the use of video lectures in the distance learning classrooms which in turn increases teacher presence and student engagement. |  | October 2017 – September 2018 |  |
| 2.1 Purchase licensing for SoftChalk, provide training, and assist instructors in the creation of course content. | Instructional Design Teams Distance Learning Technology Support Specialist Faculty Members | Establish a schedule of trainings to promote the use of Softchalk in the creation of distance learning content. Establish a method for scheduling appointments to create content using the software for those who desire instructional design assistance. | The use of this technology in the creation of content will allow increased student interaction and engagement with the content. |  | October 2017 – September 2022 (continuous) |  |
| 3.1 Purchase licensing for VoiceThread, provide training, and assist instructors in the creation of course content. | Instructional Design Teams Distance Learning Technology Support Specialist Faculty Members | Establish a schedule of trainings to promote the use of VoiceThread in the creation of distance learning content. Establish a method for scheduling appointments to create content using the software for those who desire instructional design assistance. | The use of this technology in the creation of content will allow increased student interaction and engagement with the fellow students and the instructor using audible responses. |  | October 2017 – September 2022 (continuous) |  |
| 4.1 Purchase licensing for VideoScribe, provide training, and assist instructors in the creation of course content. | Instructional Design Teams Distance Learning Technology Support Specialist Faculty Members | Establish a schedule of trainings to promote the use of VideoScribe in the creation of distance learning content. Establish a method for scheduling appointments to create lectures using the software for those who desire instructional design assistance. | The use of this technology in the creation of content will allow increased student interaction and engagement with the content. |  | October 2017 – September 2022 (continuous) |  |
| 4.2 Purchase Video Conferencing equipment, install at off-site locations, train faculty on use, train students on use | LMS Administrator Distance Learning Technology Support Specialist Faculty Members Student | Install equipment at offsite locations Establish a schedule of training for faculty and students | The installation and use of this equipment will allow offsite location enrollment numbers to grow. |  | October 2017 – September 2018 |  |
| 5.1 Hire Distance Learning Faculty Support Specialist | Executive Director, Distance Learning | Post job description, follow hire conventions | The hiring of this position will result in better trained and fully-supported distance learning faculty members which will have a direct impact on the quality of distance learning academic instruction |  | October 2017 – January 2018 (for hire) |  |
| 6.1 Purchase Grammarly subscription, train faculty and students on its use | Instructional Design Teams Distance Learning Technology Support Specialist Faculty Members Students | Establish a schedule of trainings to promote the use of the Grammarly to students and faculty | Student use of Grammarly should result in increased learner autonomy and reflect in student writing assignments |  | October 2017 – September 2022 (continuous) |  |
| 7.1 Purchase Atomic Learning subscription, train faculty and students on its use | Instructional Design Teams Distance Learning Technology Support Specialist Faculty Members Students | Establish a schedule of trainings to promote the use of the Atomic Learning to students and faculty | Student use of Atomic Learning should result in increased learner autonomy and reflect in student writing assignments |  | October 2017 – September 2022 (continuous) |  |